MadrashaOS — UI/UX Implementation Plan

Phase-by-Phase, Session-by-Session Plan to Deliver Build-Ready UI/UX

| Document | MadrashaOS_UIUX_Implementation_Plan_TechnicalDoc_2026-09-16 |
| --- | --- |
| Source | MadrashaOS Implementation-Grade SRS v2.0 (2026-09-16) |
| Author Role | Lead UI/UX Designer (Apple / Google / Tesla design heritage) |
| Audience | Project Manager, Backend Lead, Frontend Lead, Client Authority |
| Total Duration | ~5.5 weeks (8 phases, 30 sessions) |

1. Overview

This document defines the complete plan for delivering a build-ready UI/UX for MadrashaOS, a multi-tenant, multi-branch Madrasha ERP with 40+ modules across Foundation, People, Academic, Finance, Operations, Communication, and Platform layers. The plan is organized into 8 phases and 30 sessions; each session has a single objective, named inputs, concrete deliverables, and explicit exit criteria. After Session 30, the frontend and backend developers receive a complete design system, hi-fi mockups, mobile prototypes, PDF templates, and a design-QA contract — sufficient to build the entire system without further design input. Design principles: simplicity over feature-density (Apple), consistent and accessible components (Google Material, WCAG 2.1 AA per SRS §10.6), and minimal, task-focused surfaces (Tesla). The client constraint in SRS §10.8 — “not extremely complicated, not difficult for teachers or accountants, not dependent on one employee” — is the governing north star.

2. Phase Overview

| Phase | Name | Sessions | Duration |
| --- | --- | --- | --- |
| 0 | Discovery & Foundations | 0.1–0.4 | 4 days |
| 1 | Design System Foundation | 1.1–1.4 | 5 days |
| 2 | Information Architecture & Navigation | 2.1–2.4 | 4 days |
| 3 | Core Flow Wireframes | 3.1–3.4 | 5 days |
| 4 | High-Fidelity Mockups | 4.1–4.6 | 8 days |
| 5 | Print/PDF & Branding | 5.1–5.3 | 3 days |
| 6 | Prototype & Usability Validation | 6.1–6.3 | 5 days |
| 7 | Design-to-Dev Handoff | 7.1–7.4 | 3 days |

3. Design Principles (Locked in Phase 0)

Progressive disclosure: surface only what the role needs; hide advanced fields behind “More”.

One primary action per screen; secondary actions in an overflow menu (Apple pattern).

Mobile-first by default; desktop is a wider grid, not a different paradigm.

Permission-aware UI: hide, do not disable — server still enforces (SRS §5.1).

Bangla/English/Arabic first-class; RTL pipelines validated in Phase 5.

WCAG 2.1 AA contrast, keyboard navigation, screen-reader labels (SRS §10.6).

Density without clutter: 8pt grid, 4:5 content-to-whitespace ratio on desktop.

4. Phase 0 — Discovery & Foundations (4 days)

0.1 — SRS Deep-Read & Module Taxonomy

Objective: Internalize every module spec, API, UI screen, and acceptance criterion in SRS v2.0.

Inputs:

SRS Parts 2, 3, 5, 10, 11

BRD v1.0

Discovery notes on client pain points

Deliverables:

Module taxonomy spreadsheet (40+ modules, grouped by Phase 0–3)

Risk register of UX ambiguities

Exit criteria:

Designer can recite each module’s primary user, primary action, and acceptance test.

0.2 — Personas & Role Journeys

Objective: Define 8 personas (Super Admin, Authority, Administrator, Accountant, Teacher, Storekeeper, Guardian, Student) and their top-3 daily tasks.

Inputs:

SRS §8.1 role definitions

Client stakeholder interviews (2h)

Deliverables:

Persona cards with photo, goals, frustrations, tech literacy

Journey maps for: take-attendance, collect-fees, record-expense, view-child-results

Exit criteria:

Client signs off the 8 personas and 4 journey maps.

0.3 — Heuristic Review of Competing Madrasha ERPs

Objective: Benchmark 3 existing madrasha/school ERPs against 10 usability heuristics to avoid their mistakes.

Inputs:

Public demo links of 3 competing products

Deliverables:

Heuristic scorecard with screenshots

“Do-not-do” list of patterns to avoid

Exit criteria:

Avoid-list pinned to design workspace.

0.4 — Design Principles & Constraints Lock-In

Objective: Convert discovery into binding design principles and measurable constraints.

Inputs:

Outputs of 0.1–0.3

SRS §10.8 client constraint

Deliverables:

One-page design principles document (signed by client and PM)

Exit criteria:

No design work begins in Phase 1 until this page is signed.

5. Phase 1 — Design System Foundation (5 days)

1.1 — Brand Kit

Objective: Resolve SRS §11.3 open item: logo, color palette, typography stack for bn/en/ar.

Inputs:

Client brand assets (logo, preferred colors)

SRS §2.6.6 language requirements

Deliverables:

Logo set (full, monogram, favicon)

Color tokens (primary, neutral, semantic)

Typography stack: Bangla (e.g., Hind Siliguri), English (Inter), Arabic (Noto Naskh Arabic)

Exit criteria:

Tokens exported as JSON + Figma variables.

1.2 — Token System

Objective: Establish spacing, type scale, elevation, motion, and grid tokens consumed by every component.

Inputs:

1.1 brand kit

Deliverables:

8pt spacing scale

Type scale (caption→display, 6 steps)

Elevation shadows (5 levels)

Motion tokens (durations, easings)

Exit criteria:

Tokens freeze; downstream components must reference tokens, never raw values.

1.3 — Component Library v0

Objective: Build the 30 atomic components used across all 40+ modules.

Inputs:

1.2 tokens

SRS §5.2 design system requirements

Deliverables:

Buttons (primary/secondary/ghost/danger, 3 sizes, 5 states)

Inputs (text/number/date/select/textarea, with label/helper/error)

Table (sortable, paginated, sticky header, row actions)

Modal, Drawer, Toast, Tabs, Breadcrumb, Badge, Chip, Card, Skeleton, Empty state

Form layout primitives (Section, FieldRow, FilterBar)

Exit criteria:

Component spec sheet (props, states, variants) ready for frontend.

1.4 — Iconography & Illustration

Objective: Define a single icon set and 5 illustration styles for empty states.

Inputs:

1.1 brand kit

Deliverables:

Icon set (200+ icons, 24/20/16 px, stroke-based, RTL-aware)

5 empty-state illustrations (students, fees, attendance, inventory, results)

Exit criteria:

Icon font + SVG sprite generated.

6. Phase 2 — Information Architecture & Navigation (4 days)

2.1 — Module Taxonomy & Dynamic Nav Model

Objective: Design the left navigation that renders only enabled modules (SRS §2.1.2, §5.1).

Inputs:

SRS §2.1.2 module configuration

SRS §5.1 global layout

Deliverables:

Information architecture tree (3 levels max)

Dynamic nav component spec (driven by enabled-modules + permissions)

Mobile drawer variant

Exit criteria:

IA validated by card-sort with 5 madrasha staff members.

2.2 — Role-Based Dashboard Wireframes

Objective: Wireframe the 5 dashboards defined in SRS §2.6.4.

Inputs:

SRS §2.6.4

0.2 personas

Deliverables:

Authority, Accountant, Teacher, Storekeeper, Guardian dashboard wireframes

Widget inventory (12 widget types, each with empty/loading/error)

Exit criteria:

Each dashboard fits on a 1280-wide canvas without horizontal scroll.

2.3 — State System Spec

Objective: Define empty, loading, error, permission-denied, and offline states for every screen pattern.

Inputs:

SRS §5.5

Deliverables:

State spec sheet (6 states × 5 screen patterns = 30 specs)

Copy library in bn + en for each state

Exit criteria:

Frontend can implement states without further design input.

2.4 — Permission-Aware UI Rules

Objective: Translate SRS §5.1 (“hide, don’t disable”) into per-component rules.

Inputs:

SRS §5.1

SRS §6.2 permission-code list

Deliverables:

Permission-to-UI rule matrix (e.g., fees.payment.create → show Collect Payment button)

Field-level permission rules (e.g., students.notes.view → render special_notes)

Exit criteria:

Matrix reviewed and signed by backend lead.

7. Phase 3 — Core Flow Wireframes (5 days)

3.1 — Foundation Modules Wireframes

Objective: Wireframe Organization, Module Config, RBAC, Audit, Security, Backup (SRS §2.1).

Inputs:

SRS §2.1.1–2.1.6

1.3 component library v0

Deliverables:

12 wireframes (list + detail + form per module)

Audit Explorer timeline wireframe (key differentiator)

Exit criteria:

Wireframes pass cognitive walk-through with 1 accountant + 1 admin.

3.2 — People Modules Wireframes

Objective: Wireframe Student, Admission, Guardian, Teacher, Assignment, Employee (SRS §2.2).

Inputs:

SRS §2.2.1–2.2.6

Deliverables:

15 wireframes incl. Admission Kanban + Student Profile (7 tabs) + Promotion Wizard

Guardian Portal mobile wireframe

Exit criteria:

All persona top-3 tasks reachable in ≤3 clicks (SRS §10.8).

3.3 — Academic Modules Wireframes (Mobile-First)

Objective: Wireframe Academic Structure, Attendance, Examination, Results (SRS §2.3).

Inputs:

SRS §2.3.1–2.3.4

SRS §5.4 mobile considerations

Deliverables:

Routine Builder wireframe (drag-drop grid)

Take-Attendance mobile wireframe (default Present, one-tap cycle)

Marks Entry mobile wireframe (swipe-next)

Result Dashboard + printable Mark Sheet wireframe

Exit criteria:

Take-Attendance flow steps ≤6 taps for a 40-student class.

3.4 — Finance Modules Wireframes

Objective: Wireframe Fees, Scholarship, Accounting, Cash/Bank, Zakat, Donations (SRS §2.4).

Inputs:

SRS §2.4.1–2.4.6

SRS §3.6 Golden Flow

Deliverables:

Collect Payment flow wireframe (3 steps, mobile-friendly)

Ledger Explorer with running balance

Zakat dashboard (fund-isolated visualization)

Outstanding Fees report wireframe

Exit criteria:

Accountant validates the 3-step payment flow in <90s.

8. Phase 4 — High-Fidelity Mockups (8 days)

4.1 — Global Shell & Navigation Hi-Fi

Objective: Apply design system to the shell: top bar, left nav, breadcrumb, page header, footer.

Inputs:

1.x design system

2.x IA

Deliverables:

Desktop shell (1440 + 1280 breakpoints)

Mobile shell (375 + 768 breakpoints)

Language switcher interaction states (bn/en/ar + RTL)

Notification bell + user menu flyouts

Exit criteria:

Shell signed off by client; becomes the visual template for all modules.

4.2 — Foundation Module Hi-Fi

Objective: Convert foundation wireframes to hi-fi.

Inputs:

3.1 wireframes

4.1 shell

Deliverables:

12 hi-fi screens

Roles & Permissions matrix editor (interactive grid)

Audit Explorer with field-diff viewer (old → new highlighted)

Exit criteria:

Screens meet WCAG 2.1 AA contrast.

4.3 — People & Academic Hi-Fi

Objective: Convert people + academic wireframes to hi-fi.

Inputs:

3.2, 3.3 wireframes

Deliverables:

15 people screens + 12 academic screens

Student Profile tabbed interface (Personal/Academic/Guardians/Documents/Fees/Attendance/History)

Admission Kanban with drag-drop columns

Attendance mobile quick-toggles in brand colors

Exit criteria:

Teacher persona completes take-attendance in ≤60s on a 5-inch phone (SRS §2.3.2).

4.4 — Finance & Operations Hi-Fi

Objective: Convert finance + operations wireframes to hi-fi.

Inputs:

3.4 wireframes

SRS §2.5 operations

Deliverables:

18 finance + 16 operations screens

Purchase Pipeline board

Hostel Occupancy Map (visual floor plan)

Library circulation quick-scan screen

Exit criteria:

Accountant completes expense entry in ≤30s.

4.5 — Dashboards Hi-Fi

Objective: Apply design system to all 5 role dashboards.

Inputs:

2.2 dashboard wireframes

Deliverables:

5 hi-fi dashboards with 12 styled widgets

Pending Approvals widget (cross-link to Approval module)

Low-stock + outstanding-fees alert widgets

Exit criteria:

Authority dashboard’s outstanding figure reconciles to Fee module (SRS §2.6.4 acceptance).

4.6 — Mobile Screens Hi-Fi

Objective: Deliver mobile hi-fi for the 3 mobile-first workflows + guardian portal.

Inputs:

3.3, 4.3 mobile wireframes

SRS §5.4

Deliverables:

Mobile attendance (full flow, hi-fi)

Mobile marks entry (swipe-next pattern)

Guardian Portal mobile (children overview, fees, results, notices)

Responsive shell rules (breakpoint spec)

Exit criteria:

All primary CRUD actions reachable on a 5-inch phone (SRS §2.7.4).

9. Phase 5 — Print/PDF & Branding (3 days)

5.1 — PDF Templates

Objective: Design branded PDF templates for receipts, mark sheets, result sheets, certificates.

Inputs:

SRS §2.6.5

1.1 brand kit

Deliverables:

Fee receipt template (bn + en + ar)

Mark sheet + Result sheet templates

Certificate template (Phase 3 placeholder)

Ledger statement + Outstanding report templates

Exit criteria:

Arabic student name renders correctly on admission form PDF (SRS §2.6.5 acceptance).

5.2 — Public Website Templates

Objective: Design the optional public-facing site per madrasha (SRS §2.7.3).

Inputs:

SRS §2.7.3

Deliverables:

Home, Programs, Admission, Notices, Events, Contact, Donate templates

CMS admin wireframe for content editors

Exit criteria:

Public visitor cannot reach any /students, /accounts, /documents endpoint (validated by backend).

5.3 — Multi-Language Typography Validation

Objective: Validate bn/en/ar rendering across all screens and PDFs.

Inputs:

5.1, 5.2 templates

1.1 typography stack

Deliverables:

Typography QA report (line-height, fallback fonts, RTL direction)

Bangla date format (e.g., ১৬-০৯-২০২৬) validated

Exit criteria:

Zero tofu (missing-glyph squares) across bn/en/ar.

10. Phase 6 — Prototype & Usability Validation (5 days)

6.1 — Interactive Prototype

Objective: Link key flows in Figma: login → take-attendance → collect-fee → view-result → guardian-portal.

Inputs:

Phase 4 mockups

Deliverables:

Clickable Figma prototype (8 flows)

Prototype seeded with representative madrasha data

Exit criteria:

Prototype plays end-to-end without dead-ends.

6.2 — Usability Tests with Role Representatives

Objective: Run 5 moderated sessions (1 per role: Authority, Admin, Accountant, Teacher, Guardian).

Inputs:

6.1 prototype

Deliverables:

Test script per role (top-3 tasks each)

Recording + observation notes

Issue log with severity (Blocker/Critical/Major/Minor per SRS §8.4)

Exit criteria:

Blocker + Critical issues = 0 before handoff.

6.3 — Iteration & Final Spec

Objective: Fix Blockers/Criticals; freeze the design spec for handoff.

Inputs:

6.2 issue log

Deliverables:

Updated mockups (Blocker/Critical fixed)

Design spec document (component states, interaction notes, copy)

Design QA checklist for frontend

Exit criteria:

Spec frozen; further changes go through change-request process.

11. Phase 7 — Design-to-Dev Handoff (3 days)

7.1 — Design Tokens Export

Objective: Export tokens in formats consumable by frontend (CSS variables, TypeScript, Figma variables).

Inputs:

1.2 token system

Deliverables:

tokens.css, tokens.ts, tokens.json

Tailwind config preset (if frontend uses Tailwind)

Exit criteria:

Frontend imports tokens without manual mapping.

7.2 — Component Spec Sheet

Objective: Publish per-component spec: props, variants, states, accessibility roles, copy.

Inputs:

1.3 component library

6.3 final spec

Deliverables:

Component spec sheet (30 components × ~8 fields)

Storybook-ready MDX documentation

Exit criteria:

Frontend can build each component without re-asking the designer.

7.3 — Asset Library & Icon Set

Objective: Package icons, illustrations, logos, and PDF templates for dev consumption.

Inputs:

1.1 brand kit

1.4 icons

5.1 PDF templates

Deliverables:

Asset ZIP (SVG + optimized PNG + WebP)

PDF template HTML/PDF samples for backend PDF engine

Favicon + app-icon set

Exit criteria:

Backend PDF engine can ingest templates and render branded output.

7.4 — Design QA Contract

Objective: Define how design QA works during frontend build (visual review cadence, sign-off rules).

Inputs:

6.3 final spec

Deliverables:

Design QA checklist (30 items)

Review cadence (per-PR visual review, weekly holistic review)

Sign-off rule: screen not “done” until designer approves

Exit criteria:

Contract signed by designer, frontend lead, PM.

12. Handoff Deliverables (End of Phase 7)

After Session 30, the backend and frontend developers receive the following complete, build-ready package. No further design input is required for Phase 0–2 implementation:

| Design tokens | CSS + TS + JSON + Tailwind preset (Session 7.1) |
| --- | --- |
| Component library | 30 components, spec sheet, MDX docs (Session 7.2) |
| Hi-fi mockups | 70+ screens covering all 40+ modules (Phase 4) |
| Mobile prototypes | Attendance, marks entry, guardian portal (Session 4.6) |
| PDF/print templates | Receipts, mark sheets, certificates, reports (Session 5.1) |
| Public website templates | 7 pages + CMS admin (Session 5.2) |
| Design QA contract | Per-PR review rules + sign-off process (Session 7.4) |
| Multi-language assets | bn/en/ar validated, RTL pipelines confirmed (Session 5.3) |

13. Next Step

Kick off Phase 0 Session 0.1 immediately. The SRS is already in hand; stakeholder interviews (Session 0.2) require the client to schedule 2 hours with one representative per role. Once Phase 0 ends with the signed design-principles page, the designer works independently through Phases 1–7 and re-engages the client only at: Phase 4 sign-off (shell + dashboards), Phase 6 usability tests, and Phase 7 handoff. This plan closes the open visual-design item in SRS §11.3 and produces a UI/UX that the backend and frontend developers can build against without further design iteration.